This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point featur
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works we
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to imple
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for eac
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to imple
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for eac
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to imple
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for eac
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to imple
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for eac
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to imple
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for eac
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to imple
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for eac
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day
## Product Backlog
Product Name:	JADE Manager					Complete Fields in Green!!!
Team ID:	Covefe					Sprints / Features Remaining at end of Sprint

	Team Member Name					Initials	Student ID
Required	Ethan Jobe					EAJ	1001871601

	Updated for Sprint 4

Sprint #	Remaining	Completed This Sprint			Comment
0	21			Total	Total number of features (in column H)
1	18	3		1	Total features left at the end of Sprint #1
2	16	2		2	Total features left at the end of Sprint #2
3	13	3		3	...and so on
4	11	2
5	9	2
6	8	1

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints		Features are always graded at the end of the sprint in which they are required, regardless of when they are implemented
Feature ID	Priority	Required	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
CF	1	1	13	1	Finished in Sprint 1	Manager	Create a new coffee flavor	Stock and sell coffee products
CC	2	1	5	1	Finished in Sprint 1	Manager	Create a new donut	Stock and sell donuts
STOR	3	1	13	1	Finished in Sprint 1	Manager	Manage a list of coffee and donut products per store	Manage training and advertising
GUI	4	2	8	2	Finished in Sprint 2	Manager	Use a main window (GUI) with simple menu bar tool bar	Reduce training costs	This is the main window, with just a menu bar (for now). For this sprint, you can just hard-code or randomly create java and donuts
IGUI	5	2	21	2	Finished in Sprint 2	Manager	Use dialogs to create new coffee and donut products	Reduce training costs	Sequence of dialogs OK for initial prototype. One dialog each for coffee and for donuts is below.
CE	6	3	13	3	Finished in Sprint 3	Manager	Create a new store	Franchise JADE operations	This includes all data in a store, including new features implemented in later sprints
SAVD	7	3	8	3	Finished in Sprint 3	Manager	Save all data to a default file on exit or command	Ensure our data isn’t lost	This includes all data in a store, including new features implemented in later sprints
LOAD	8	3	5	3	Finished in Sprint 4	Manager	Load data from a default file on startup	Ensure our data isn’t lost	This includes all data in a store, including new features implemented in later sprints
SALL	9	3	5	3	Finished in Sprint 3	Owner	Save all data to a specified file	Franchise my company	Use the File Chooser dialog (see Lecture 15)
LALL	10	3	5	3	Finished in Sprint 4	Owner	Load data from a specified file	Franchise my company	Use the File Chooser dialog (see Lecture 15)
UD	11	4	21	4	Finished in Sprint 5	Manager	Create unified dialogs across the application	Interact more efficiently with the program	Each command (e.g., Create > Donut) should required a single dialog
CB	12	4	8	4	Finished in Sprint 5	Server	Create a new beloved customer	Keep track of our customers
CS	13	5	3		In Work	Server	Create a new named server	Track server productivity and tips
CO	14	5	8		In Work	Server	Create an order of multiple products	Serve everyone in a customer party	Use a HashMap with Product index and int quantity value
PS	15	5	5		In Work	Customer	List all coffee and donut products in a dialog	See what the Customer can order	This is probably a combobox of each Product’s toString
POC	16	5	3		In Work	Customer	Show the servings in an order for the customer (what was ordered / how much it costs)	Verify that my order was taken correctly and see the price	This can simply be text in a MessageDialog, or something snazzier; probably similar to and maybe identical to Feature PS
CSB	17	5	8		In Work	Customer	Associate the order with a customer	Self-order and not have to deal with people	“What name should I put on the ticket” so they can call for you when your order is ready. This also practices Map.
CSS	18	5	2		In Work	Customer	Associate the order with a server	Order via a server so that they receive credit	“What name should I put on the ticket” so they can call for you when your order is ready. This also practices Map.
P&L	19	6	8		Finished in Sprint 6	Manager	Add a Profit & Loss statement, showing all income, expenses, and total profit	Ensure that we’re making a profit and thus avoid bankruptcy	Demonstrate the use of Java iterators with this feature
RTM	20	6	8		In Work	Manager	Display a Server Report, listing all info about each server including # of orders served	Better manage our team and reward productive team members	Demonstrate the use of Java iterators with this feature
EF	21	6	8		In Test	Manager	Edit a product	Improve our data and keep it synced to reality

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 05		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 12
Demo on	TBD		Days / Tasks

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Not assigned due to error.
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Oct 12		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 19
Demo on	TBD		Days / Tasks

	Remaining	Completed (this day)
Total Tasks	11
Day 1 Left	11	0
Day 2 Left	11	0
Day 3 Left	7	4
Day 4 Left	2	5
Day 5 Left	2	0
Day 6 Left	1	1
Day 7 Left	0	1

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	IGUI	EAJ	combo box donut enums, onCreateDonutClick()	Completed Day 3
2	GUI	EAJ	menu bar (not including functionality)	Completed Day 3
3	IGUI	EAJ	get donut price, cost, name with JOptionPane	Completed Day 3
4	IGUI	EAJ	boolean sprinkles check boxes	Completed Day 3
5	GUI	EAJ	create tool bar	Completed Day 4	action event should just call over to create donut and create java
6	GUI	EAJ	File -> quit (fix)	Completed Day 6
7	IGUI	EAJ	about page	Completed Day 4
8	IGUI	EAJ	create price, cost, name and combo box in the java portion	Completed Day 4	easy, can knock out very quick tomorrow
9	IGUI	EAJ	Shots in Java	Completed Day 4
10	IGUI	EAJ	addProduct() implementation after creating donut/java object	Completed Day 4
11	GUI	EAJ	JLabel the list of selected products	Completed Day 7	JLabel works now
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Oct 19		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 26
Demo on	TBD		Days / Tasks

	Remaining	Completed (this day)
Total Tasks	6
Day 1 Left	6	0
Day 2 Left	6	0
Day 3 Left	6	0
Day 4 Left	6	0
Day 5 Left	3	3
Day 6 Left	3	0
Day 7 Left	2	1

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CE	EAJ	File>Create NEW empty store	Completed Day 7
2	LOAD	EAJ	File>OPEN, choose dialog to load up data	In Work	Edit Buffered Reader to read new information.
3	savd	EAJ	File>save to most recent file	Completed Day 5
4	sall	EAJ	File>Save as a new file with new name	Completed Day 5
5	GUI	EAJ	Update menu bar items (NEW OPEN SAVE SAVE AS)	Completed Day 5
6	LALL	EAJ	Load file on startup	In Work	Does not load up most recent file upon startup.
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 02		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 09
Demo on	TBD		Days / Tasks

	Remaining	Completed (this day)
Total Tasks	11
Day 1 Left	10	1
Day 2 Left	10	0
Day 3 Left	10	0
Day 4 Left	10	0
Day 5 Left	10	0
Day 6 Left	7	3
Day 7 Left	2	5

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	UD	EAJ	unified dialog	Completed Day 7
2	CB	EAJ	create new customer	Completed Day 1
3	UD	EAJ	onCreateCustomerClick() method	Completed Day 7
4	CB	EAJ	Create new customer gui (tool & menu bar)	Completed Day 6
5	CB	EAJ	Customer buffered reader/writer	Completed Day 6
6	CB	EAJ	View Products (calls update Display)	Completed Day 7
7	CB	EAJ	View People (calls different update Display)	Completed Day 7
8	CB	EAJ	JDialog onCreateCustomerClick	Completed Day 6
9	UD	EAJ	Jdialog for creating java	In Work
10	UD	EAJ	JDialog for creating donut	In Work
11	CB	EAJ	JDIalog for creating java (SHOTS)	Completed Day 7
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 09		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 16
Demo on	TBD		Days / Tasks

	Remaining	Completed (this day)
Total Tasks	9
Day 1 Left	9	0
Day 2 Left	9	0
Day 3 Left	9	0
Day 4 Left	9	0
Day 5 Left	6	3
Day 6 Left	6	0
Day 7 Left	6	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	UD	EAJ	Remaining features from sprint 4	Completed Day 5	Unified dialog needs to be finished and working. New update display must be made
2	CB	EAJ	Remaining features from sprint 4	Completed Day 5	View customer must be made, utilizes the new update display!
3	CS	EAJ	create server	Completed Day 5
4	CO	EAJ	create order	In Work
5	PS	EAJ	update display, put inside of dialog..	In Work
6	POC	EAJ	show servings(total price, what was ordered, etc)	In Work
7	POC	EAJ	add more of the same listed products to order	In Work
8	CSB	EAJ	associate order with customer	In Work
9	CS	EAJ	css* associate order with server	In Work
10		EAJ		In Work
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 30		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Dec 07		NOTE: A stand-alone assignment on threading is Nov 16-30
Demo on	TBD		Days / Tasks

	Remaining	Completed (this day)
Total Tasks	6
Day 1 Left	6	0
Day 2 Left	6	0
Day 3 Left	6	0
Day 4 Left	5	1
Day 5 Left	3	2
Day 6 Left	3	0
Day 7 Left	3	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CO	EAJ	Fix create coffee (shots and name not displaying)	In Work	Low priority.
2	CO	EAJ	Fix creating an order (Does not have working functionality)	In Work	Lower priority.
3	EF	EAJ	Create Edit on tool bar: Edit>Product>Donut/Java	Completed Day 4	Needs to update the previous selected item. Only adds onto the list. Works halfway as of right now.
4	P&L	EAJ	Create Reports > Profit & Loss (Displaying a table)	Completed Day 5
5	RTM	EAJ	Display the P&L table	Completed Day 5
6	RTM	EAJ	Report > Server Menu Item > Displays SSN, server, name	In Work
7		EAJ
8		EAJ
9		EAJ
10		EAJ
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84